## Sheet1
|  | March | [25 empty] | April | [29 empty] | May
|  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
|  | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12
| Assignment Deadlines | April M 10: A-2; May S 14: A-3
Task-ID | User Story ¯ | March M 6: People Management Planning; March M 13: Software Design; March M 20: Team Structure & Governance; March M 27: Scope Planning; April M 3: Schedule Planning; April M 10: Budget Planning; April M 17: Risks Mgt Planning; April M 24: Procurement; May M 1: Quality & Performance Planning; May M 8: Project Security & Integration Management; May M 15: Week 12
A2-U1 | People Mgt | March M 6: Sprint 1; March M 13: Sprint 2; March M 27: Sprint 3
A2-U2 | Team Structure & Governance, etc | March M 20: Sprint 1; March M 27: Sprint 2
A2-U3 | A-2 Review | April M 3: Sprint 1
A2-U4 | Final Edit, Proof-read & Submit (~UAT) | April T 6: Sprint 1
A-2 Product Delivery
A3-U1 | Software Design | March M 13: Sprint 1; March M 20: Sprint 2
A3-U2 | Scope Planning | March M 27: Sprint 1; April M 3: Sprint 2; April M 17: Sprint 3
A3-U3 | Schedule Planning | April M 3: Sprint 1; April M 10: Sprint 2; April M 24: Sprint 3
A3-U4 | Budget Planning | April M 10: Sprint 1; April M 17: Sprint 2; April M 24: Sprint 3
A3-U5 | Risks Mgt Planning | April M 17: Sprint 1; April M 24: Sprint 3
A3-U6 | A-3 Report Review | May M 1: Sprint 1
A3-U7 | Final Edit, Proof-read & Submit (~UAT) | May W 10: Sprint 1
A-3 Product Delivery
A-2 Work Tracker Work Items
A2-U1 | People Mgt Sprint 1 | March M 6: Sprint 1; March M 20: Standup Meet 1
A2-U1 | People Mgt Sprint 2 | March M 13: Sprint 2; March M 27: Standup Meet 2
A2-U1 | People Mgt Sprint 3 | March M 27: Sprint 3
A2-U2 | Team Structure & Governance, etc Sprint 1 | March M 20: Sprint 1
A2-U2 | Team Structure & Governance, etc Sprint 2 | March M 27: Sprint 2; April M 3: Standup Meet 3
A2-U3 | A-2 Review | April M 3: Sprint 1
A2-U4 | Final Edit, Proof-read & Submit (~UAT) | April T 6: Sprint 1
A-2 Product Delivery
A-3 Work Tracker Work Items
A3-U1 | Software Design Sprint 1 | March M 13: Sprint 1
| Software Design Sprint 2 | March M 20: Sprint 2
A3-U2 | Scope Plan Sprint 1 | March M 27: Sprint 1
| Scope Plan Sprint 2 | April M 3: Sprint 2
| Scope Plan Sprint 3 | April M 17: Sprint 3
A3-U3 | Schedule Plan Sprint 1 | April M 3: Sprint 1
| Schedule Plan Sprint 2 | April M 10: Sprint 2
| Schedule Plan Sprint 3 | April M 24: Sprint 3
A3-U4 | Budget Planning | April M 10: Sprint 1
Sprint 2
Sprint 3
A3-U5 | Risks Mgt Planning | April M 17: Sprint 1
Sprint 3
A3-U6 | A-3 Report Review | May M 1: Sprint 1
A3-U7 | Final Edit, Proof-read & Submit (~UAT) | May W 10: Sprint 1
A-3 Product Delivery
Work Tracker Attributes to be setup in Work Tracker
Task ID
Work Item (User Stories)
Assigned to (Person or Group)
Category (Sprint)
Progress (Not Started, In Progress, Completed, Behind)
Priority (to completion) - Critical, High, Medium, Low, <completed>
Start Date (original)
End Date (original)
Revised End-Date
Delay & Other Notes